## Bug Report
Bug Report
Quality Assurance - QA | [10 empty] | Dev
Bug ID | Module Name | Build no. | Description | TC ID | Steps to replicate bug | Screenshot | Severity | Priority | Reported by | Assigned to | Resolution | Status | Fixed date
ORHRM_001 | Orange HRM-my info | 1 | Dashboard is displayed instead of MyPageInfo after login is successfull | TC_MYINFO_001 | 1.) launch broswer 2.) Open URL "http://opensource-demo.orangehrmlive.com" 3.) Provide valid ESS user name 4.) Provide valid password 5.) Click on Login button | printscreen of the bug | S3 | P3 | Sangeeta | Dev. Colleague | accepted | InProgress
ORHRM_002 | Orange HRM-my info | 1 | The mssg of 'invalid file type' should appear after selecting the the wrong file. Instead it uploads the the file and then displays the mssg that file is not supported. | TC_MYINFO_008 | 1.) Login to HRMorange as ESS user 2.)Click on MyInfo tab 3.) Click on the photo at the corner of the screen 4.) Click on broswe and then select the photo from a relevant path 5.)Click upload after selecting the picture | printscreen of the bug | S3 | P3 | Sangeeta | Dev. Colleague | accepted | open
ORHRM_003 | Orange HRM-my info | 1 | Can not save the license, because we can not select license type from the drop box | TC_MYINFO_35 | 1.) Login to HRMorange as ESS user 2.)Click on MyInfo tab 3.) Click on Qualifications link 4.) Click on ADD button under License 5.) Click save once all the fields are entered | printscreen of the bug | S3 | P3 | Sangeeta | Dev. Colleague | accepted | open
ORHRM_004 | Orange HRM-my info | 1 | Can not save the license, because we can not select license type from the drop box | TC_MYINFO_36 | 1.) Login to HRMorange as ESS user 2.)Click on MyInfo tab 3.) Click on Qualifications link 4.) Click on ADD button under Licenses 5.) Click save once all the fields are entered | printscreen of the bug | S3 | P3 | Sangeeta | Dev. Colleague | accepted | open
ORHRM_005 | Orange HRM-my info | 1 | Can not delete the license, because we can not select license type from the drop box, thus there are no listed licenses | TC_MYINFO_37 | 1.) Login to HRMorange as ESS user 2.)Click on MyInfo tab 3.) Click on Qualifications link 4.)Under licenses, click on the box next to the entry you want to delete 5.) Click on delete | printscreen of the bug | S3 | P3 | Sangeeta | Dev. Colleague | accepted | open